SCRUM CARD GAME
The Manual
(с) Timofey (Tim) Yevgrashyn, 2010
Version 3.1, July 2016
See http://scrumcardgame.com for updates and additional materials.
(с) review / correction / completion, Oliver Merkel, November 2016
SCRUM CARD GAME by Timofey (Tim) Yevgrashyn is licensed under a Creative Commons
Attribution-ShareAlike 4.0 International License.
You have permission to use, copy and redistribute the material in any medium or format
and
also
remix,
transform,
and
build
upon
the
material
for
any
purpose,
even
commercially.
Under the following terms:
Attribution — You must give appropriate credit, provide a link to the license, and
indicate if changes were m
ade.
ShareAlike — If you remix, transform, or build upon the material, you must distribute your
contributions under the same license as the original.
To view a copy of this license, visit http://creativecommons.org/licenses/by-sa/4.0/.
This work is licensed under the Creative Commons Attribution-ShareAlike 4.0 International
License. To view a copy of this license, visit http://creativecommons.org/licenses/by-sa/4.0/.

---
What is SCRUM CARD GAME?
SCRUM CARD GAME is a simple game, which lets players experience work in Scrum sprints
and brings to discussion many questions and topics that happen in real life while working
in a Scrum team. Even the discussion on the table will be very close to the real-life
experience of the work in a scrum team. This game is usually played during a training or
workshop. Participants must already have an understanding of the Scrum framework. Or
you should introduce them to the framework right before the game. They can learn more
while playing this game. It might also be a useful method to make an experienced team
reflect on their established scrum rituals and rules.
Split the audience into teams of 4-5-6 people, equally if possible. No more than six players
per team.
Set the Goal: You are competitive development centers aimed to deliver a new
application to the market. The most productive team wins :-)
Game Set
Set of cards: Stories, Events, Problems, and Solutions (see printable version below)
●
Two six-sided dice (per each team)
●
Flip chart
●
Markers or post-its
●
Preparation
Provide each team with a set of Story cards
●
Cards with stories forming the “Backlog” deck
○
Backlog is prioritized (sequence number in top corner) and estimated
○
(hours in bottom corner)
3 days per iteration (there will be maximum 3 iterations)
○
Every iteration consists of:
○
Planning and commitment
■
Work within iteration
■
Sprint Review + Retrospective
■
Make the group arrange a simple Task Board by marking TODO, IN PROGRESS,
●
DONE columns with simple sticky notes to visualize their state.
Prepare a flip chart list with visualization of PLAN and ACTUAL columns for each
●
team in play.
This work is licensed under the Creative Commons Attribution-ShareAlike 4.0 International
License. To view a copy of this license, visit http://creativecommons.org/licenses/by-sa/4.0/.

---
Planning
Ask teams “how many features do you believe you can deliver in the next
●
iteration?”
In the first round let every team calculate their number of man-hours per
iteration as they would like to do. Allow them to make even optimistic
commitment :)
○
To perform 2nd and 3rd planning you ask teams to use historical data.
○
Put selected cards from “Backlog” into TODO column.
●
Write down commitment as the total number of estimates and numbers of Stories
●
of every team on a f
lip chart into “Plan” column.
Work each Day within iteration
Each iteration consists of three days. Each day consists of every team-member working
on the sprint.
It starts with player 1 “working” on the sprint. If the last member of the team “worked”
the first day has ended. Now the same for day two and three starts. “Working” in the
sprint is described below. Every team member in their turn should:
Select a Story to work on (it should appear in “IN PROGRESS”) and make this
choice visible by pointing on the card with the finger.
●
Roll two dice to determine the number of productive hours of this team-member
●
on this day
Hand over two dices on the first round right after explaining this step
○
Deduct number on the dice from remaining hours on the card (s)he “works on”
●
Advise players to calculate remaining as it helps to avoid mistakes
○
To simplify tracking participants can stick a post-it on a card and write
○
remaining time there
Pull the card from the “Chance” deck
●
Hand over the “Chance” deck on the first round right after explaining this
○
step
Do whatever the card says. There are three possible types of cards:
●
Event - a one-time action, that affects immediately and discarded after the
○
play
Problem - these sticky issues are blocking the Story that the player was
○
“working on”. Each problem is a case taken from the real life, a team could
bring examples or details in
to each Problem from their experience.
Blocking means the team can’t move the story into DONE state, they
■
have to find a Solution for the kind of problems stated on a card.
Blocking doesn’t prevent from continue work on a Story (deducting hours
■
until zero).
This work is licensed under the Creative Commons Attribution-ShareAlike 4.0 International
License. To view a copy of this license, visit http://creativecommons.org/licenses/by-sa/4.0/.

---
Sometimes, positive Events could also help with Problems :-)
■
Solutions - A solution is a team’s asset or action which can be applied at
○
any time to solve a problem and unblock a Story. Once Solution applied
the Problem and Solution cards are discarded.
Solutions could be collected by the team if there are no appropriate
■
Problems - they are collected from iteration to iteration and belong to
the whole team.
If User Story is done (0 hours remaining and no
blockers) - move it to DONE column.
●
DONE criteria for a Story:
●
Team members delivered the number of hours equal or greater than estimate
○
for a Story
A Story is not blocked with a Problem.
○
Once again, at every “day” each player does follow:
●
Choose a card to “work on”
●
Throw two dices
●
Pick a Chance card
Sprint Review + Retrospective
After each player has passed 3 turns - the Sprint is over.
●
Each team should present Stories accomplished (i.e. only
 stories in DONE column)
●
and calculate the actual result as the total of DONE Stories.
Compare Actual result with initial Plan.
●
Review undone work and discuss the reason, also discuss how to account these
●
undone Stories in next Sprint to make sure we maintain the total number from the
original estimations.
Retrospect on how to perform in next Sprint to achieve more.
●
Debriefing
To start debriefing you should bring in front of the audience the flip chart(s) with visualizing
all Planned and Actual data for each of three sprints.
Here are some topics to
Planned vs Actual
●
Velocity variations
●
Hours Estimate vs Size (Original Estimate)
●
Major risks happened (Technical, People, Unplanned Events)
●
What are the hardest types of risks to take?
●
Could we forecast bad events?
●
and etc…
●
This work is licensed under the Creative Commons Attribution-ShareAlike 4.0 International
License. To view a copy of this license, visit http://creativecommons.org/licenses/by-sa/4.0/.

---
About Timofey Yevgrashyn
I’m an experienced Agile Manager with consulting, coaching and training expertise.
My personal experience in IT industry starts back at 1998, from which more than 12 years
I had been managing effective software teams and most of the time with Agile methods.
Over last eight years, I am sharing the knowledge and experience as a Trainer, Agile
Coach, and Consultant.
I have proven track record of launching and leading Agile/Lean transformations that
lead to aligning delivery with business goals. By 2016 I have helped to more than 50 teams
from over 10 countries, done about 3000 hours of Agile training for over 4000 people.
My
specialties:
Agile
and
Lean
based
processes,
Agile
Product
Management,
Organizational Culture transformation, Leadership Coaching.
My work is always pragmatic and practical and training is more an interactive workshop
than just a theory. I’m a big fan of education with games and is the author of several
Agile games.
Since
2009,
I
write
for
my
Russian-speaking
blog
“The
Improved
Methods”
(http://tim.com.ua) to popularize Agile/Lean mindset and methods on Eastern Europe.
Also,
I’m
an
experienced
public
speaker
participated
in
international
and
local
conferences. You can find the archive of slides on my site. Or simply invite me to your
conference for the talk or a workshop :-)
About Oliver Merkel
I am an Electrical Engineer and Computer Science guy. Currently not really in need for any more sophisticated advertising. Still if you appreciate my work then tell me or better tell others about it. All hands person. Actively developing in embedded systems writing boot scripts, boot loaders, hardware abstraction, driver development, up to application development and architectural stuff in various team sizes and set ups. Doing stuff professionally like holding training sessions, consulting, live agile methods, doing management, project and team leads, and developing long enough so to know what I am doing. There might be ways to bribe me.
Be creative... :-)
This work is licensed under the Creative Commons Attribution-ShareAlike 4.0 International
License. To view a copy of this license, visit http://creativecommons.org/licenses/by-sa/4.0/.

---
STORY
#1
24
Users can exchange emails
securely with predefined
recipients.
STORY
#2
21
Users can send large files securely.
STORY
#3
27
Users can set time limits on emails
for reading.
STORY
#4
30
Users can send emails securely to
unspecified recipients.
STORY
#5
16
Administrators of organizations
can monitor emails.
STORY
#6
24
Each organization can set security
policy and define recipients
groups.
STORY
#7
43
Users can manage their emails
effectively.
STORY
#8
23
Users and administrators can
backup emails securely.
STORY
#9
36
Users and administrators can
delete emails completely.
STORY
#10
68
Users can access emails from
mobile.

---
EVENT
EVENT
GURU
A guru visited your office. You may
immediately remove one problem
card from the current story.
EVENT
EVENT
EVENT
EVENT
EVENT
HEALTH PROBLEM
Health problem.
Skip your next turn.
EVENT
GOOD RECRUIT
New recruit is good.
You may roll 2 dice now and add
these to the last roll.
STORY
#11
28
Users can send short messages
securely to each other.
STORY
#12
24
Users don’t want to receive spam-
letters.
VISIBLE EFFORT
The boss acknowledges
your effort. You may add 3 points
to the previous result.
EMERGENCY CALL
An emergency call.
Everyone skips next turn.
HOME OFFICE
You worked well at home. Add 2
points to the last roll.
FAIRY
A fairy helped you.
A card in progress is instantly
finished.
DOING WELL
Things are going
incredibly well.
Add 4 to the last roll.

---
EVENT
EVENT
EVENT
EVENT
EVENT
EVENT
PROBLEM
PROBLEM
PROBLEM
OVERTIME
You worked overtime.
Draw another card and
follow its instruction.
REQUIREMENTS CHANGE
PO decided to make changes to
the project. So this story will take 4
hours more.
BIRTHDAY
It’s your birthday today. Subtract 1
point from everybody’s next result.
HARD DRIVE CRASHED
Hard drive crashed.
Remove all progress
from a card in progress.
BUSINESS TRIP
You are sent on a business trip.
Skip next turn.
EXTRA COST
Your work costs more than
planned. Add 6 hours to the story
estimation.
PROBLEM
TECHNICAL OBSTACLE
Your work is blocked by a technical
obstacle.
UNCLEAR SPEC
The specification is not clear
enough for you.
UNSATISFIED USERS
You feel that users are not satis-
fied.
BAD QUALITY
You cannot finish the story
because the quality is inadequate.

---
PROBLEM
PROBLEM
PROBLEM
PROBLEM
PROBLEM
PROBLEM
SOLUTION
SOLUTION
SOLUTION
SOLUTION
DATA IS MISSING
You can’t work with the story, as
you don’t have important data
from PO.
BAD MOOD
Today you are upset. So you are too
lazy to work.
BAD COMMUNICATION
You cannot communicate well with
other team members. They just
don’t get you.
POOR SKILLS
You are not skilled enough to finish
the work.
UNSTABLE SYSTEM
System is very unstable. You test
with major difficulties.
INTEGRATION ISSUES
Your colleague provided you with
the component, which is different
from what you expected. You can’t
proceed.
GET SOME REST
Get some rest to refresh your mind.
EXTRA MEMBER
Add another member to the team.
Throw dice at any moment you
want.
SPECIALIST
Engage a specialist.
INSIGHT
Apply your insight.

---
SOLUTION
SOLUTION
SOLUTION
SOLUTION
SOLUTION
SOLUTION
SOLUTION
SOLUTION
EVENT
BROWN BAG MEETING
Discussion during lunch time led
to a splendid idea. Work on the
current card is instantly resolved.
add-on
SKILLED MEMBER
Involve skilled team member from
other team.
COMMUNICATION
Enhance communication.
AUTOMATED TESTING
Introduce automated testing.
COLLABORATION
Get the team together with PO and
exchange important information.
SHARE GOALS
Get the team together and share
the key project goals.
INVOLVE BOSS
Your boss is ready to take a part of
the work.
ENHANCE SKILLS
Training for raising the level of your
skill.
PAIR PROGRAMMING
Apply pair programming.